## To Do List
|  | To do list |  |  |  |  | SETUP >
2018-12-23
| Due Today: | 3
| Overdue: | 0
| Done | Description | Due Date | Priority | Assigned to | Date Modify | Update
Tip: Enter a number greater than 1 in Done column when task is complete. | 1 | Requirement 1 | 2018-12-23 | High | Ho Tan Viet | 2018-12-21 | Ho Tan Viet
| 1 | Requirement 2 | 2018-12-22 | High | Nguyen Phan Quoc Thinh | 2018-12-21 | Nguyen Phan Quoc Thinh
|  | Requirement 3 | 2018-12-23 | High | Bui Anh Tuan | 2018-12-21 | Bui Anh Tuan
| 1 | Requirement 4 | 2018-12-23 | High | Nguyen Huu Nhan | 2018-12-21 | Nguyen Huu Nhan
| 1 | Layout Design | 2018-12-22 | High | Nguyen Phan Quoc Thinh | 2018-12-22 | Nguyen Phan Quoc Thinh
| 1 | Checklist Code | 2018-12-22 | High | Nguyen Huu Nhan | 2018-12-22 | Nguyen Huu Nhan
| 1 | Task | 2018-12-22 | Low | Nguyen Phan Quoc Thinh | 2018-12-22 | Nguyen Phan Quoc Thinh
|  | Guide Line | 2018-12-23 | Low | Bui Anh Tuan | 2018-12-23 | Bui Anh Tuan
| 1 | Requirement 5 | 2018-12-22 | High | Nguyen Huu Nhan | 2018-12-22
|  | Requirement 6 | 2018-12-23 | High |  | 2018-12-23
| 1 | Code APK | 2018-12-23 | High |  | 2018-12-23
Enter a number 1 in Done column when task is complete
Select a drop down arrow, such as Assigned To or Priority, to Filter or Sort your To Do List items.
Tips do not print.

## Assignment Setup
Assignment Setup | < TO DO LIST
The data in the table below supplies all the works we do in Software Engineering project
Assigned To
Nguyen Huu Nhan
Nguyen Phan Quoc Thinh
Bui Anh Tuan
Ho Tan Viet